## Read Me
Topic | Guidance
Purpose | Enterprise release-management capability catalog and proposed agent architecture. 56 use cases, 9 logical agent roles. Broad reference catalog, not a universal exhaustive list or an installed product claim.
Scope | Plan/change, build, environments, security, validation, readiness, deployment/recovery, communication, measurement and agent governance. Release Management coordinates; specialist owners retain operational control.
How to use | Filter Use Cases by wave, owner, phase and agent. Agree service criticality and change policy; baseline data quality; assign local tools and an accountable owner. Cross-reference UC and A IDs in diagram/playbooks.
Implementation assumption | Tool-neutral design. Optional mappings to ServiceNow, Entra/SailPoint, Azure APIM/AgentGateway and Splunk/Dynatrace are examples only; licensing, APIs, versions and exact controls require local validation.
Architecture rule | Agents reason, explain and propose. A durable workflow owns state, a policy engine owns deterministic authorization, humans own approvals, and scoped controllers execute. Logical agents need not be separately deployed services.
Automation boundary | Do not use an LLM to verify signatures, count DORA metrics, enforce a spend ceiling or make irreversible rollback decisions. Use deterministic code and policy; agents may explain outcomes.
Source interpretation | S01-S10 are research references in Sources. Source links support underlying practices, not the invented agent taxonomy or every workflow design. Design marks original synthesis requiring local validation.
Risk and score caveat | No universal risk score, canary threshold, time window, savings estimate or ROI is asserted. Thresholds and weights must be calibrated on service-level data and approved by owners.
Validation | Workbook and draw.io XML are structurally checked. Diagram has not been visually rendered in diagrams.net; edit labels/layout as needed.
Research date | 2026-10-29. Distinguish source-specific versioned guidance from enterprise architecture recommendations.

## Use Cases
Use case ID | Phase | Use case | Agent ID | Execution pattern | Where implemented | Accountable stakeholder | Work with | Trigger and required inputs | What should be done | Expected outcome | Measure / KPI | Guardrails / human boundary | Wave | Source IDs
UC01 | Plan & Change | Change scope drift detection | A03 | Agent-assisted + deterministic workflow | ITSM change workflow + deployment admission | Change Manager | Release Manager; service owner; platform | Approved change baseline; current manifest; deployment request | Compare artifact digests, services, environments, windows and configuration with approved scope; flag delta and request reassessment | Unapproved scope changes held before deployment | Unauthorized-scope deployment rate | Invalidate approval on material scope change; never auto-expand scope | 1 | S01;S07
UC02 | Plan & Change | Runtime-to-approved change reconciliation | A03 | Agent-assisted + deterministic workflow | Deployment events + CMDB/ITSM reconciler | Change Manager | SRE; CMDB owner; audit | Observed deployment/config events; approved records | Match actual changes to authorized release; open discrepancy with evidence | Unrecorded or out-of-window changes visible | Unmatched deployments per 100 deployments | Read-only detection first; no destructive auto-reversion | 1 | S01
UC03 | Plan & Change | Release risk signals and explanation | A03 | Agent advisory; human/policy decides | Release intelligence service | Release Manager | AppSec; QA; SRE; product | Diff size; dependency fan-out; incident history; test freshness; SLO burn; rollback readiness | Compute versioned rule-based signals; explain contributing evidence; calibrate any predictive model later | Explainable risk recommendation, not opaque approval | Failure rate by risk tier; false-negative rate | Missing evidence = unknown; model score cannot override mandatory gates | 1 | S03;S06
UC04 | Plan & Change | Change classification recommendation | A03 | Agent advisory; human/policy decides | ITSM change intake | Change Manager | Service owner; CAB/policy owner | Change type rules; service criticality; previous approved patterns | Recommend standard/normal/emergency route with rationale | Consistent routing with fewer manual handoffs | Routing agreement rate; intake lead time | Only approved change policy can classify automatically; emergency route retained | 1 | S01
UC05 | Plan & Change | Release calendar and freeze conflicts | A03 | Agent advisory; human/policy decides | ITSM release calendar | Release Manager | Business operations; SRE; portfolio | Release windows; freeze calendar; shared-service changes | Detect overlaps, blackout breaches and on-call conflicts; propose alternatives | Fewer conflicting releases | Conflict-related incidents; scheduling wait | Authorized exception required during freeze | 1 | Design
UC06 | Plan & Change | Cross-service sequencing and dependency graph | A03 | Agent advisory; human/policy decides | Release planner + service catalog | Release Manager | Architects; API owners; DBAs | Version contracts; service dependencies; migration requirements | Build release DAG; detect cycles and incompatible sequencing; recommend waves | Explicit dependency-safe rollout plan | Dependency-caused failures | Owner validates graph freshness and critical edges | 2 | Design
UC07 | Plan & Change | Emergency release coordination | A03 | Agent advisory; human/policy decides | ITSM emergency path + incident workflow | Incident Commander | Change Manager; SRE; security; business | Incident severity; emergency policy; candidate fix | Assemble minimum mandatory evidence, emergency authorization and post-review tasks | Fast but auditable emergency delivery | Emergency lead time; overdue reviews | No bypass by model; named emergency approver and expiring exception | 2 | S01
UC08 | Plan & Change | Release manifest and traceability graph | A03 | Agent-assisted + deterministic workflow | Release manifest service + evidence store | Release Manager | SCM; CI/CD; platform; audit | Commits; build IDs; digests; IaC revision; flags; change ID | Create immutable versioned manifest linking code, artifacts, config and approvals | Single release identity across systems | Manifest completeness; orphan artifact rate | Digest-addressed references; mutation creates new manifest revision | 1 | S02;S08
UC09 | Build | Pipeline-as-code generator | A01 | Agent-assisted + deterministic workflow | SCM PR + approved template catalog | CI/CD Platform Owner | AppSec; developers; platform | Service type; approved pipeline templates; repo policy | Generate pipeline YAML via approved components; lint, test and open PR | Standardized maintainable pipelines | Onboarding lead time; template adoption | No unreviewed production credentials; validate external actions and versions | 2 | S01;S10
UC10 | Build | Bounded self-fixing PR loop | A01 | Agent-assisted + deterministic workflow | Isolated CI remediation worker | Engineering Lead | CI/CD owner; code owners; AppSec | Failed job logs; repo snapshot; allowed paths | Classify failure; propose patch; run sandbox tests; retry within configured limit; open PR | Faster recovery from known CI failures | Time to green; accepted-fix rate | Example limit: 2 attempts and fixed token/runtime budget; no own merge, policy edits or secret access | 2 | S10
UC11 | Build | Build critical-path optimization | A01 | Agent-assisted + deterministic workflow | CI analytics + SCM PR | CI/CD Platform Owner | Developers; QA; FinOps | Job DAG; duration; compute cost; test dependencies | Identify bottlenecks; propose safe parallelization and runner sizing; benchmark | Reduced build latency and waste | p50/p95 pipeline duration; cost/build | Must preserve required checks and validate equivalent outputs | 2 | Design
UC12 | Build | Dependency cache management | A01 | Deterministic automation primary; agent explains/proposes | CI cache service + artifact repository | CI/CD Platform Owner | AppSec; repository owner | Lockfiles; toolchain version; cache keys; trust boundary | Implement scoped keys, trusted writer rules, expiry and poisoning checks; measure hits | Faster trustworthy builds | Cache hit ratio; clean-vs-cached output mismatches | Separate untrusted PR cache from protected builds; never cache secrets | 2 | S01
UC13 | Build | Runner capacity and queue management | A01 | Deterministic automation primary; agent explains/proposes | CI runner autoscaler | CI/CD Platform Owner | Platform; FinOps | Queue length; job demand; runner quotas | Forecast demand; adjust within predefined pool and cost caps | Lower queue delay | p95 queue wait; utilization | Deterministic upper bounds; isolated ephemeral runners | 2 | S09
UC14 | Build | Pipeline policy drift detection | A01 | Agent-assisted + deterministic workflow | SCM policy scanner + CI admission | CI/CD Platform Owner | AppSec; change management | Approved templates; current YAML; branch protections | Detect disabled gates, unpinned actions and privilege expansion; open remediation PR | Pipeline controls remain intact | Policy compliance; remediation time | Agent cannot modify policy baseline or approve exception | 1 | S01;S10
UC15 | Build | Artifact reproducibility and immutability | A01 | Deterministic automation primary; agent explains/proposes | Build service + registry promotion | Build Engineering Owner | AppSec; artifact repository owner | Build inputs; digest; provenance; target environment | Promote the same verified digest; compare controlled rebuilds where supported | No environment-specific artifact substitution | Digest consistency across stages | Never use mutable tag alone for authorization | 2 | S07;S08
UC16 | Environment | Ephemeral environment provisioning | A02 | Agent-assisted + deterministic workflow | IaC workflow + developer platform | Platform Owner | QA; developers; security; FinOps | Approved blueprint; PR ID; data classification; TTL | Plan, policy-check, provision approved test environment and register owner/expiry | Repeatable preview environments | Provision lead time; orphan cost | Nonproduction only initially; lease and cleanup; deny unsafe data | 2 | S01;S09
UC17 | Environment | Environment configuration drift | A02 | Agent-assisted + deterministic workflow | GitOps/IaC drift detector | Platform Owner | SRE; change management | Desired IaC/config; observed runtime; approved exceptions | Compare state; explain impact; PR or approved reconciliation | Reduced environment drift | Drift age; unapproved drift count | Known emergency changes reconciled before overwriting | 1 | Design
UC18 | Environment | Platform compliance scanner | A02 | Deterministic automation primary; agent explains/proposes | IaC checks + runtime posture scan | Platform Security Owner | AppSec; SRE; audit | Control baseline; resource inventory; scan evidence | Run deterministic checks; agent groups findings and proposes remediations | Policy-compliant release environments | Compliance coverage; finding age | LLM explanation is not control evidence; approved exceptions expire | 1 | S01
UC19 | Environment | Secrets and certificate readiness | A02 | Deterministic automation primary; agent explains/proposes | Secret manager metadata + readiness gate | Security Operations Owner | IAM; SRE; service owners | Expiry metadata; workload identity bindings; secret references | Validate referenced credentials, expiry horizon and rotation readiness | Fewer credential-related release failures | Expiry-related incidents; readiness failures | Do not provide secret values to models; use scoped metadata APIs | 1 | S10
UC20 | Environment | Environment reservation and contention | A02 | Deterministic automation primary; agent explains/proposes | Test environment scheduler | QA Platform Owner | QA teams; platform; Release Manager | Test windows; lease state; shared resources | Detect contention; reserve environment; release lease after run | Predictable integration testing | Reservation wait; collisions | Leases idempotent and expiring; owner for overrides | 2 | Design
UC21 | Environment | Capacity forecasting and headroom | A08 | Agent advisory; human/policy decides | Metrics warehouse + capacity planner | Platform Owner | SRE; FinOps; product | Demand seasonality; load tests; rollout surge; quotas | Forecast service demand with interval; test peak and canary surge capacity | Capacity-backed release plan | Forecast error; saturation incidents | Forecast advisory; load test and quota gate authoritative | 2 | S06;S09
UC22 | Environment | Pre-deployment cost and allocation guard | A08 | Deterministic automation primary; agent explains/proposes | Provisioning/pipeline admission + allocation ledger | FinOps Owner | Platform; budget owner; Release Manager | IaC cost estimate; reserved allocation; quotas; resource/SKU policies | Reserve bounded allocation atomically; deny excess new capacity; reconcile actual usage | Bounded new provisioning exposure | Rejected excess allocation; estimate error | Not a guaranteed cloud invoice cap; delayed billing and ongoing resources remain | 2 | S09
UC23 | Environment | Environment teardown and data sanitation | A02 | Deterministic automation primary; agent explains/proposes | Lease controller + IaC destroy workflow | Platform Owner | Data owner; QA; security | Lease expiry; environment inventory; retention policy | Delete eligible ephemeral resources; verify cleanup and data disposition | Reduced orphan spend and data exposure | Expired-resource cost; cleanup success | Exclude production/shared dependencies; approval for retained data deletion | 2 | S09;S01
UC24 | Security | SAST/SCA/DAST findings triage | A04 | Agent advisory; human/policy decides | Security findings aggregator + PR | AppSec Owner | Developers; QA; service owner | Scan outputs; reachability; deployment context | Deduplicate and prioritize with evidence; propose fixes and verified retests | Faster security remediation | Time to remediate; triage precision | Cannot mark finding fixed without scanner/retest evidence | 1 | S01
UC25 | Security | SBOM completeness and vulnerability release gate | A04 | Deterministic automation primary; agent explains/proposes | CI + registry promotion gate | AppSec Owner | Legal; developers; registry owner | SBOM; vulnerability feeds; accepted exceptions | Validate coverage and policy findings; block per approved severity/context rules | Known supply-chain exposure handled before release | SBOM coverage; policy-block escapes | Deterministic decision; signed expiring exception for waiver | 1 | S02;S07
UC26 | Security | Artifact signature and provenance verification | A04 | Deterministic automation primary; agent explains/proposes | Registry promotion + deployment admission | Supply Chain Security Owner | Build engineering; platform | Artifact digest; attestation; trusted builders; signature trust roots | Verify digest binding, signatures, builder and allowed parameters | Only trusted artifacts promoted | Rejected untrusted artifacts; verification coverage | Generating provenance alone is insufficient; verification must fail closed | 1 | S07;S08
UC27 | Security | License and third-party usage checks | A04 | Agent advisory; human/policy decides | Dependency gate + legal workflow | Open Source Program Owner | Legal; procurement; AppSec | Dependency inventory; license rules; usage context | Identify policy conflicts and route legal review | Reduced license exposure | Unreviewed restricted dependencies | No model-only legal decision; legal exceptions recorded | 2 | S01
UC28 | Security | Security waiver lifecycle | A04 | Agent advisory; human/policy decides | ITSM exception workflow + release gate | Risk Acceptance Owner | AppSec; service owner; audit | Finding; compensating controls; expiry; signed approval | Draft exception, track scope/expiry, reject stale waiver and schedule remediation | Time-bound explicit risk acceptance | Expired waivers used; overdue remediation | Agent cannot approve its own waiver; bind to release/control scope | 1 | S01;S10
UC29 | Security | Post-release vulnerability impact mapping | A04 | Agent advisory; human/policy decides | SBOM index + runtime inventory | AppSec Owner | SRE; incident response; service owners | New vulnerability; deployed digests; SBOMs | Identify affected deployments; notify owners and open remediation changes | Faster exposure response | Time to affected-service identification | Confirm inventory freshness; protect sensitive dependency data | 2 | S02
UC30 | Validate | Risk-based test selection recommendation | A09 | Agent advisory; human/policy decides | CI test planner | QA Owner | Developers; AppSec; service owner | Changed paths; dependency graph; test history; critical controls | Recommend additional impacted tests and test ordering | Faster focused validation | Escaped defects; test duration | Must not remove mandatory tests; coverage model must be validated | 2 | S01
UC31 | Validate | Flaky test diagnosis | A09 | Agent advisory; human/policy decides | Test analytics + SCM PR | QA Owner | Developers; CI/CD owner | Repeated runs; nondeterminism evidence; test logs | Explain likely causes and propose fixes; rerun on clean runner | More reliable quality signals | Flake rate; false-block time | Quarantine only under owner-approved policy; never silently suppress | 2 | Design
UC32 | Validate | API and event contract compatibility | A09 | Deterministic automation primary; agent explains/proposes | Contract registry + CI gate | API Owner | Consumers; architects; QA | Schemas; consumer contracts; version policy | Run compatibility checks; map impacted consumers and propose sequence | Fewer breaking integration releases | Contract-break escapes | Deterministic checks; consumer approval for intentional break | 1 | Design
UC33 | Validate | Database and data migration safety | A09 | Deterministic automation primary; agent explains/proposes | Migration rehearsal + release gate | Database Owner | Data engineering; SRE; application owners | Migration scripts; restore test; compatibility matrix | Rehearse expand/contract; evaluate locks, data loss and forward recovery | Explicit data-safe deployment plan | Migration incidents; rehearsal pass rate | App rollback does not undo schema/data changes; DBA approval for destructive changes | 1 | Design
UC34 | Readiness | Release readiness scorecard | A03 | Agent advisory; human/policy decides | Release portal + evidence aggregator | Release Manager | QA; AppSec; SRE; product; Change Manager | Tests; verified artifacts; capacity; approvals; runbooks; telemetry freshness | Calculate each control state and evidence age; summarize blockers | Auditable go/no-go recommendation | Evidence completeness; readiness wait | Statuses pass/fail/unknown/waived; critical fail/unknown cannot be averaged away | 1 | S01;S06;S07
UC35 | Readiness | SLO and error-budget release gate | A03 | Deterministic automation primary; agent explains/proposes | Observability query + deployment gate | Service Owner | SRE; product; Release Manager | SLO burn; incidents; service policy | Evaluate approved release eligibility and route exceptions | Release pace aligned to reliability | Burn-related blocks; post-release SLO breach | Thresholds service-specific; stale telemetry holds promotion | 1 | S06
UC36 | Readiness | Rollback and recovery rehearsal | A05 | Agent-assisted + deterministic workflow | Staging deployment workflow | SRE Owner | DBA; platform; QA | Stable digest; backup/restore evidence; rollback runbook | Test traffic rollback, flag disable and restoration paths; record limitations | Verified recovery readiness | Rehearsal pass rate; measured recovery time | Include config/data compatibility; cannot assume every release reversible | 1 | S04;S05
UC37 | Readiness | On-call and operational handover | A03 | Agent advisory; human/policy decides | Service catalog + ITSM gate | Service Owner | SRE; support; Release Manager | Runbook; on-call roster; dashboards; escalation | Validate coverage, support documentation and service ownership | Operable release with clear responders | Unowned releases; handover completeness | Roster evidence must be current; do not infer acceptance from silence | 1 | Design
UC38 | Readiness | Policy authorization and approval binding | A03 | Deterministic automation primary; agent explains/proposes | External policy engine + ITSM + deployment admission | Change Manager | IAM; AppSec; platform; audit | Manifest digest; environment; window; policy version; approver decision | Evaluate mandatory controls and verify exact authorized action before execution | Enforceable approval rather than chat-based consent | Approval-scope mismatch escapes | Separate proposer/approver/executor; new material scope requires new authorization | 1 | S10;S07
UC39 | Deploy & Recover | Canary release orchestration | A05 | Deterministic automation primary; agent explains/proposes | Deployment controller + traffic manager | SRE Owner | Release Manager; service owner; platform | Verified artifact; approved plan; analysis metrics | Controller executes traffic steps and analysis; agent diagnoses anomalies | Smaller initial blast radius | Canary-detected regressions; exposure before abort | Minimum samples/dwell; stable cohort; missing metrics pause; no LLM traffic control | 2 | S04;S06
UC40 | Deploy & Recover | Blue-green release and cutover | A05 | Deterministic automation primary; agent explains/proposes | Deployment controller + load balancer | Platform Owner | SRE; DBA; service owner | Parallel stack; smoke results; cutover authorization | Validate new stack; controller switches traffic; retain old stack within window | Controlled cutover and recovery path | Cutover errors; recovery duration | State synchronization and capacity validated; immutable artifact binding | 2 | S04
UC41 | Deploy & Recover | Feature flag rollout and kill switch | A05 | Deterministic automation primary; agent explains/proposes | Feature management service | Product Owner | SRE; developers; Release Manager | Cohort policy; flag owner; success/error metrics | Progressively enable feature; disable via preapproved safety policy | Separate deployment from feature exposure | Feature-related incidents; stale flag age | Flags versioned/audited; sensitive targeting protected; cannot reverse data effects | 2 | Design
UC42 | Deploy & Recover | Multi-region wave orchestration | A05 | Deterministic automation primary; agent explains/proposes | Release workflow + regional controllers | SRE Owner | Regional operations; platform; business | Region health; version skew limits; dependencies | Roll out in approved waves with inter-wave verification | Regional blast radius limited | Regions impacted per failure | Respect residency and active-active compatibility; explicit pause points | 3 | Design
UC43 | Deploy & Recover | Health and regression detection | A05 | Deterministic automation primary; agent explains/proposes | Observability analysis service | SRE Owner | Data analysts; QA; product | Error/latency/saturation; business KPIs; control cohort | Evaluate baseline deltas; detect anomalies; correlate with release | Earlier credible regression signals | Detection time; false abort rate | Distinguish missing data from healthy; minimum traffic/sample rules | 1 | S06
UC44 | Deploy & Recover | Rollback decision and execution boundary | A05 | Agent-assisted + deterministic workflow | Policy engine + controller + incident workflow | Incident Commander | SRE; DBA; service owner; Change Manager | Failed health gate; stable target; recovery constraints | Recommend recovery; controller aborts or rolls back only when preauthorized; escalate unsafe cases | Fast bounded recovery with accountability | Failed deployment recovery time; unsafe rollback count | No autonomous destructive DB rollback; validate target compatibility; persist incident evidence | 2 | S03;S04;S05
UC45 | Deploy & Recover | Post-rollback Git and ITSM reconciliation | A05 | Deterministic automation primary; agent explains/proposes | GitOps desired-state PR + ITSM update | Platform Owner | SRE; Change Manager; developers | Controller stable state; Git desired revision; incident | Align desired state through approved revert/fix PR; update change and incident | Avoid repeated redeploy of failed revision | Reintroduced failed versions | Argo runtime rollback does not change Git; block unintended re-promotion | 2 | S05
UC46 | Communicate & Close | Release notes generation | A06 | Agent advisory; human/policy decides | SCM + release portal + knowledge base | Release Manager | Product; engineering; legal; support | Merged PRs; issues; manifest; known limitations | Draft audience-specific notes with linked evidence and compatibility warnings | Consistent accurate release communication | Editing effort; factual correction rate | Review customer-visible content; redact secrets and internal findings | 1 | Design
UC47 | Communicate & Close | Stakeholder notifications and release status | A06 | Agent-assisted + deterministic workflow | ITSM + collaboration integration | Release Manager | Support; business; SRE; product | Lifecycle events; subscription rules; approvals | Draft/send approved templates with state links and owner escalation | Timely targeted updates | Notification latency; duplicate rate | Recipient allowlist; idempotent sends; review external/freeform content | 1 | Design
UC48 | Communicate & Close | Audit evidence packet | A06 | Agent-assisted + deterministic workflow | Immutable evidence store + ITSM attachments | Compliance Owner | Release Manager; AppSec; audit; platform | Control results; approvals; digests; timestamps; execution events | Assemble verifiable evidence index with lineage and retention metadata | Lower audit effort and traceable decisions | Evidence retrieval time; completeness | Preserve source evidence; hash and timestamp; no model-authored proof | 1 | S02;S08
UC49 | Communicate & Close | Change closure and CMDB reconciliation | A06 | Deterministic automation primary; agent explains/proposes | ITSM closure workflow + observed deployment inventory | Change Manager | CMDB owner; service owner; SRE | Observed versions; validation result; acceptance; linked incidents | Reconcile deployed state and draft closure; close only under policy | Accurate inventory and change outcomes | CMDB freshness; closure lag | Do not mark successful on pipeline completion alone; service validation required | 1 | Design
UC50 | Measure & Improve | DORA measurement and metric lineage | A07 | Deterministic automation primary; agent explains/proposes | Event warehouse + BI | Engineering Productivity Owner | Release Manager; developers; SRE | Commit/build/deployment/incident events; service map | Calculate five DORA measures with versioned definitions and joins | Consistent delivery performance visibility | Metric data completeness; join accuracy | Service/team measures not individual ranking; retain denominator and exclusions | 1 | S03
UC51 | Measure & Improve | Flow bottleneck and waiting-time analysis | A07 | Agent advisory; human/policy decides | Workflow event analytics | Release Manager | Engineering managers; QA; change management | State transitions; approval queues; CI durations | Separate work time from waiting; explain major bottlenecks | Targeted process improvements | Median/p95 release lead time; wait ratio | Validate cause hypotheses with teams; correlation is not causation | 2 | S03
UC52 | Measure & Improve | Incident-to-release learning loop | A07 | Agent advisory; human/policy decides | Incident knowledge base + backlog PRs | SRE Owner | Developers; AppSec; Release Manager | Postmortem; release graph; root-cause evidence | Propose tests, policy/template improvements and runbook updates | Fewer recurrent failure modes | Repeat incidents; action completion | Blameless review; no automatic punitive changes to team scores | 2 | S01;S03
UC53 | Measure & Improve | Sprint velocity reporting, optional | A07 | Agent advisory; human/policy decides | Team-local work tracker analytics | Engineering Manager | Product owner; Scrum team | Completed work; team estimates; sprint definitions | Report team-local trend separately from release throughput and forecast uncertainty | Local planning support without misleading comparison | Forecast accuracy within same team | Not a release gate or cross-team productivity rank; not a DORA metric | 3 | S03
UC54 | FinOps | Release cost anomaly detection | A08 | Agent advisory; human/policy decides | Cost/usage telemetry + release manifest join | FinOps Owner | Platform; service owner; Release Manager | Cost exports; real-time usage proxy; release time; resource tags | Compare post-release cost/unit and usage with baseline; propose remediation | Earlier detection of inefficient releases | Cost/unit delta; detection lag | Billing data delayed; validate attribution; no blind production shutdown | 2 | S09
UC55 | FinOps | Compute/resource right-sizing proposals | A08 | Agent advisory; human/policy decides | Capacity planner + IaC PR | Platform Owner | FinOps; SRE; QA | Utilization; latency; SLOs; unit economics | Suggest bounded sizing changes; load-test and open IaC PR | Lower cost without reducing reliability | Cost/unit at agreed SLO | No direct production downsize by agent; retain headroom and rollback path | 3 | S09;S06
UC56 | Governance | Release agent assurance and evaluation | A06 | Agent-assisted + deterministic workflow | Agent platform + security evaluation pipeline | Agent Platform Owner | AppSec; IAM; Release Manager; audit | Tool scopes; model/prompt version; evaluation set; execution trace | Evaluate hallucination, injection, permission boundaries and task success before promotion | Governed agents with measurable safety | Unauthorized-action attempts; groundedness; regression pass rate | Short-lived identity; deny by default; approval outside model; kill switch and full trace | 1 | S10

## Agent Catalog
Agent ID | Logical agent | Accountable owner | Responsibilities | Tools / data surfaces | Authority boundary | Use case mapping
A01 | Pipeline Engineering | CI/CD platform owner | Pipeline generation, bounded self-fix, build and cache optimization | SCM, CI runners, template registry | PR proposal; sandbox tests; no own-PR approval | UC09-UC15
A02 | Environment & Platform | Platform engineering owner | Provisioning, drift, capacity and environment readiness | IaC, cloud APIs, GitOps, CMDB | IaC PR; approved nonproduction execution; no direct production shell | UC16-UC23
A03 | Release Intelligence & Coordination | Release Management owner | Readiness, risk explanation, calendar and dependencies | ITSM, service catalog, release manifest, evidence store | Read/recommend; never manufacture or grant approval | UC01-UC08; UC34-UC38
A04 | Security & Supply Chain | AppSec owner | Finding triage, remediation proposals, evidence gaps | SAST/SCA/DAST, registry, SBOM/provenance verifier | Explain and propose; deterministic security gate is authoritative | UC24-UC29
A05 | Progressive Delivery & Recovery | SRE / service owner | Rollout plan recommendation, health diagnosis, recovery recommendation | Deployment controller, feature flags, observability | Controller executes preauthorized bounded rollout/abort; human for irreversible recovery | UC39-UC45
A06 | Release Communications & Evidence | Release Management owner | Draft notes, stakeholder updates, evidence packets and closeout | SCM, ITSM, knowledge base, evidence store | Draft then review externally visible messages; no fabricated evidence | UC46-UC49; UC56
A07 | Delivery Analytics | Engineering productivity owner | Delivery metric explanations and bottleneck hypotheses | Event warehouse, SCM/CI/CD events, incidents | Read-only; deterministic metric calculation | UC50-UC53
A08 | FinOps & Capacity Advisor | FinOps owner | Cost forecast, rightsizing and budget exception recommendation | Cost exports, usage metrics, provisioning estimator | Advisory; policy/admission and reservation ledger enforce limits | UC21; UC22; UC54-UC55
A09 | Test & Compatibility Advisor | QA engineering owner | Risk-based test recommendations, flaky test diagnosis, compatibility impact | Test platform, contract registry, migration tools | Propose tests; cannot delete required tests or waive failed controls | UC30-UC33

## Execution Playbooks
Playbook | Agent | Trigger | Required context | Execution steps | Authoritative gates | Tool adapters needed | Limits and permissions | Failure and escalation | Output evidence | Use case IDs
P01 | A01 | CI failure or onboarding request | SCM commit SHA + pipeline/job ID | Read logs with secret redaction; classify; select approved template or bounded patch; run sandbox CI; create PR | Deterministic lint, required tests, code-owner approval | SCM PR API; CI dispatch; template registry | Max attempts/runtime/tokens; no own merge or gate edits | Stop after bound; attach evidence; route to code owner | PR diff; test results; tool trace | UC09;UC10;UC14
P02 | A01 | Pipeline performance review | Job DAG + trusted cache namespaces | Benchmark baseline; propose DAG/runner/cache change; compare clean/cached results; PR | Required checks unchanged; cache trust verified | CI analytics; cache API; SCM | Cache separation; checksum/lockfile keys; spend quota | Revert config PR on regression; disable compromised namespace | Duration/cost baseline; cache hit data; output checks | UC11;UC12;UC13
P03 | A02 | Environment request or drift event | Blueprint revision + environment ID + lease owner | IaC plan; compliance and cost admission; reserve allocation; apply via controller; register lease; verify; teardown at expiry | Approved blueprint and allowed scope; production approval distinct | IaC runner; cloud provisioning; CMDB | Least privilege; idempotency key; no secret values in context | Compensate partial provisioning; retain incident record; avoid shared-resource delete | Plan digest; policy verdict; execution record; expiry | UC16;UC17;UC18;UC23
P04 | A03 | Candidate release or scope update | Versioned manifest digest + change ID | Join source evidence; check freshness; compute readiness states and risk reasons; route missing controls; request approval | Mandatory fail/unknown blocks; approval bound to exact scope | ITSM read/workflow; evidence store; policy evaluation | No self-approval; policy source immutable to agent | Hold release and route to accountable control owner | Per-control status; timestamps; source links; approved manifest | UC01;UC03;UC08;UC34;UC38
P05 | A04 | Build candidate or new vulnerability | Artifact digest + SBOM + trusted provenance | Run deterministic verification/scanners; correlate context; propose remediation/waiver draft; reverify | Trusted signature/builder; vulnerability and license policy | Registry; scanner APIs; policy engine | Model cannot declare signature valid or grant waiver | Quarantine candidate; route AppSec; expire exception | Verifier logs; scan run IDs; signed exception if any | UC24;UC25;UC26;UC28;UC29
P06 | A05 | Approved release dispatch | Manifest digest + target + approved rollout plan + policy revision | Controller validates approval; deploy small cohort; collect minimum samples; evaluate analysis; promote/pause/abort | Fresh telemetry; approved steps; budget/capacity; compatible stable target | Deployment controller; traffic/flags; observability | Only preauthorized bounded actions; no arbitrary shell or direct model traffic commands | Pause on inconclusive data; safe abort if preauthorized; otherwise page incident commander | Step history; metric queries/results; artifact identities | UC39;UC40;UC41;UC42;UC43
P07 | A05 | Regression or failed analysis | Current/stable digests + schema/config compatibility + incident ID | Classify fault; evaluate safe recovery options; deterministic controller abort if authorized; DBA/human decision for data recovery; reconcile desired Git state | Recovery plan and authority; irreversible recovery requires explicit owner approval | Rollout controller; ITSM incident; SCM revert PR | Rollback binary != restore data; no direct destructive database tool | Stop rollout; route traffic to compatible stable target where safe; escalate uncertainty | Decision reason; exact action; health after recovery; Git reconciliation | UC36;UC44;UC45
P08 | A06 | Approved release or state transition | Release manifest + approved audience + source PR/issues | Draft notes/status; link facts; redact; review; publish via workflow; assemble evidence; validate service then close | Human review for external freeform content; source evidence retained | SCM; ITSM; knowledge base; messaging connector | Allowlisted recipients; idempotent sends; no invented test or approval evidence | Keep draft if evidence missing; update correction log | Reviewed text; recipients; publication ID; immutable evidence index | UC46;UC47;UC48;UC49
P09 | A07 | Daily/weekly analytics event | Normalized commit/deploy/incident events + metric definition version | Deduplicate; join service IDs; calculate DORA deterministically; segment failures; agent explains bottlenecks | Data quality checks; documented denominators and observation period | Event warehouse; BI; work tracker | No individual rankings; velocity not comparable between teams | Mark incomplete periods; do not infer missing incidents as zero failures | Lineage; denominator; excluded events; metric version | UC50;UC51;UC52;UC53
P10 | A08 | Provisioning plan or spend/usage anomaly | Estimate + allocation ledger + workload demand | Forecast cost; reserve allocation atomically; policy denies excess capacity; monitor usage; propose right-sizing PR | Admission limits plus approved exceptions; production shutdown separate | Cost exports; quotas; provisioning gate; ledger | No absolute invoice-cap promise; forecasts advisory; preserve critical availability | Deny new allocation at limit; alert owner; release unused reservations | Estimate/reservation IDs; admission verdict; actual-vs-estimate | UC21;UC22;UC54;UC55
P11 | A09 | PR test planning or migration request | Diff + contracts + test history + migration script | Recommend tests; run required suites; diagnose flakes; check contracts; rehearse migration and recovery | Mandatory tests always required; DBA decision on destructive migration | Test executor; contract checker; staging DB tools | Read-only production data; masked test sets; cannot waive tests | Hold candidate and route QA/API/DB owner | Test run IDs; contract verdict; migration rehearsal evidence | UC30;UC31;UC32;UC33

## Risk and Gates
Signal | What is measured | Evidence source | Decision rule (calibrate locally) | Action | Decision owner | Use cases
Scope drift | Approved vs requested artifact/service/env/window/config | Change baseline + release manifest | Any material unmatched difference | Hold; reassess risk and approval | Change Manager | UC01
Artifact trust | Digest, provenance signature, builder and expected parameters | Trusted verifier + registry | Verification failure or missing required attestation | Block promotion/deployment | Supply Chain Security | UC26
Security exposure | Policy-defined severity/context and waiver validity | Scanner evidence + exception registry | Unaccepted prohibited finding or expired waiver | Block; route AppSec/risk owner | AppSec | UC25;UC28
Test evidence | Required suite completion and freshness for exact candidate | CI test results bound to SHA/digest | Missing/stale/failed required tests | Hold; unknown is not pass | QA | UC30;UC34
Migration risk | Backward compatibility; lock duration; tested restore/forward fix | Migration rehearsal + DBA review | Destructive or incompatible unapproved change | Require DBA-approved migration/recovery plan | Database Owner | UC33
Operational health | Error-budget burn, active incident, capacity and quota | Observability + incident + quota APIs | Breach of service-specific release policy | Hold or authorized exception | Service Owner/SRE | UC21;UC35
Canary regression | Latency/errors/saturation/business metric deltas vs baseline | Fresh telemetry with cohort labels | Approved threshold breached with sufficient samples | Controller pause/abort under authorized plan | SRE | UC39;UC43
Insufficient telemetry | Freshness; sample count; query errors; cohort attribution | Metric queries + data quality checks | Missing, inconclusive or too little traffic | Pause promotion; investigate; do not claim healthy | SRE | UC39;UC43
Readiness model | Control states + evidence age + criticality | Versioned release evidence index | Any mandatory fail or unknown blocks; waiver only if allowed | Publish recommendation with reasons; external authorization decides | Release Manager | UC34
Cost risk | Estimated incremental cost, reserved allocation, current usage | IaC estimate + ledger + cost/usage export | Admission limit exceeded or unexplained cost/unit rise | Deny new allocation or propose change; no blind shutdown | FinOps/Platform | UC22;UC54

## Data and Event Contracts
Contract | Minimum fields | Required invariants | Owner | Use case mapping
Release manifest | release_id; revision; manifest_digest; service_ids; commit_SHA; artifact_digests; IaC/config/flag revisions; target_env; window; change_id; rollout/recovery_plan refs | Immutable revisions; approvals and evidence bind to digest; store sensitive refs not secrets | Release coordinator | UC08;UC38
Evidence record | evidence_id; release_id; subject_digest; control_id; result; produced_at; valid_until; source_uri; source_run_id; collector_identity; content_hash | Pass/fail/unknown/waived; verify source integrity; TTL per control; retention by policy | Evidence collector | UC34;UC48
Authorization decision | decision_id; manifest_digest; action; resource/target; time_window; policy_version; approver_identity; approval_time; expiry; exception_refs | Signed or tamper-evident; exact-scope comparison at dispatch and step boundaries; invalidate on material mutation | Policy/ITSM owner | UC01;UC38
Tool invocation envelope | request_id; correlation_id; release_id; agent_identity; delegated_scope; action; target; argument_hash; idempotency_key; deadline; authz_ref | Target-side authorization; short-lived credentials; schema validation; environment boundary; trace of outcomes | Agent platform/IAM | UC56
Lifecycle event | event_id; event_type; occurred_at; service_id; release_id; artifact_digest; environment; source; source_sequence; schema_version; parent_event_id | At-least-once delivery; dedup by event_id; tolerate late/out-of-order events; transactional outbox where needed | Platform/event owner | UC45;UC50
Workflow state machine | DRAFT > BUILT > VERIFIED > READY > AUTHORIZED > DEPLOYING > OBSERVING > ACCEPTED > CLOSED; alternates HELD/ABORTED/RECOVERING/FAILED | Durable workflow state not LLM memory; explicit transitions, timeouts, retries and compensations; reconcile external state | Release platform owner | All
Cost reservation | reservation_id; scope; owner; estimated_rate; duration/TTL; allocation_units; policy_limit; approved_exception; expiry; actual_usage_ref | Atomic reservations avoid concurrent over-allocation; limits on admitted resources are not guaranteed currency caps | FinOps/platform | UC22

## Governance Controls
Control | Required design | Implementation examples (validate locally) | Owner | Acceptance test
Identity | Each agent/workflow has an owned non-human identity; use federated or short-lived credentials; separate environments | Entra/IAM; access governance e.g. SailPoint where configured | IAM | Test token audience, expiration and cross-environment deny
Tool enforcement | Authorize each action and target outside model; tool schemas and allowlists; prevent arbitrary SQL/shell | AgentGateway/tool wrapper + target-side IAM; APIM for appropriate API policies | Security/Platform | Attempt unauthorized tool, scope escalation, parameter injection
Separation of duties | Proposer cannot approve own code, production release or exception | SCM protections + ITSM approval + deployment admission | Change Manager | Mutate manifest after approval; verify dispatch denies
Untrusted content | Treat logs, PR text, documents and tool results as data; redact secrets; constrain retrieval | Agent runtime sandbox and tool adapter | AppSec | Prompt injection corpus from build logs and PR descriptions
Deterministic authority | Policy engine, signature verifier, CI and controllers enforce gates; model scores advisory | Policy as code + CI/CD/admission | Platform | Model recommends bypass; gate still blocks
Resilience | Durable workflow, idempotency, retry caps, dead-letter queue, reconciliation and kill switch | Workflow service + event bus | Platform | Duplicate events; timeout after successful action; kill switch exercise
Audit | Capture source evidence, model/prompt versions, tool args/results with redaction and policy decisions | Evidence store + Splunk/Dynatrace or existing telemetry | Audit/SRE | Trace approved release from commit to observed runtime
Access revocation | Recheck policy at privileged steps; expire grants and cache decisions; stop future actions after revocation | IAM + gateway + target system | IAM/Platform | Revoke access mid-workflow; distinguish in-flight request from next-step deny
Evaluation | Version model/prompts/tools; test correctness, injection, unauthorized actions, cost, latency and task success | Agent assurance pipeline | Agent Platform | Compare shadow-mode decisions with expert review before expanding autonomy

## Adoption Roadmap
Wave | Theme | Illustrative scope | Deliverables | Stakeholders | Exit criteria (set targets locally) | Autonomy
1 | Foundation and observe | UC01-UC03;UC08;UC14;UC17-UC20;UC24-UC26;UC28;UC32-UC38;UC43;UC46-UC50;UC56 | Release ID and manifest; evidence collectors; read-only risk/readiness; deterministic mandatory gates; metric baseline; agent identity and eval | Release Mgmt + platform + IAM + AppSec + SRE | Evidence traceability validated; unauthorized mutation denied; shadow-mode false negatives reviewed; local success thresholds agreed | No autonomous production changes; review content and proposals
2 | Bounded proposals and controlled execution | UC06-UC07;UC09-UC13;UC15-UC16;UC21-UC23;UC27;UC29-UC31;UC39-UC41;UC44-UC45;UC51-UC52;UC54 | Sandbox PR remediation; ephemeral provisioning; allocation admission; canary and authorized abort; Git reconciliation | Platform + engineering + QA + FinOps + SRE | Test blast radius and kill switch; rehearsal succeeds; telemetry reliable; rollback limitations documented; human signoff on autonomy scope | Nonproduction first; prod only deterministic approved controller actions
3 | Advanced optimization | UC42;UC53;UC55; calibrated predictive risk extension | Multi-region waves; capacity/cost optimization; predictive risk only with labeled outcomes and drift monitoring | SRE + FinOps + analytics + service owners | Demonstrated measured benefit vs baseline; bounded failure rate; model calibration and attribution reviewed | Keep high-risk approval and irreversible changes human-controlled

## Metric Definitions
Metric | Definition | Data required | Caveats | Sources
Change lead time | Time from version-control commit to production deployment | Commit timestamps joined to production deployment events | Service/team, consistent merge/commit semantics | S03
Deployment frequency | Production deployments per period, or time between deployments | Successful production deployment events; consistent deployment unit | Service/team; distinguish deployments from feature releases | S03
Failed deployment recovery time | Time to recover from a deployment that failed and needed immediate intervention | Incident/recovery event linked to failed deployment | Do not replace with generic incident MTTR | S03
Change fail rate | Deployments requiring immediate intervention / all deployments in the same scope and period | Linked incident, rollback or hotfix evidence; deduplicated deployment IDs | Define intervention and observation window; late incidents may revise prior period | S03
Deployment rework rate | Unplanned incident-driven deployments / all deployments in the same scope and period | Incident-linked unplanned deployment classification | Distinct from failed deployment count; retain classification evidence | S03
Readiness completeness | Controls with valid evidence / required controls; report missing mandatory controls separately | Evidence freshness and exact candidate binding | Completeness does not equal approval or safety | Design
Change drift escape rate | Observed deployments outside approved material scope / observed deployments | Approved manifests vs runtime events | Report unmatched inventory and data-quality gaps | Design
Agent fix acceptance | Accepted independently reviewed fixes / proposed fixes | SCM review/merge and CI outcome | Pair with escaped defects, attempts, cost and unauthorized action rate | Design
Release cost efficiency | Attributed incremental release/runtime cost per agreed business unit | Tagged resource usage/cost and business-volume metrics | Attribution assumptions explicit; billing delay limits near-real-time claims | S09;Design

## Sources
ID | Source title | URL | How used
S01 | NIST SSDF project | https://csrc.nist.gov/projects/ssdf | Security practices and release provenance
S02 | NIST SP 800-218 v1.1 | https://nvlpubs.nist.gov/nistpubs/specialpublications/nist.sp.800-218.pdf | Secure development, archive and provenance practices
S03 | DORA software delivery performance metrics | https://dora.dev/guides/dora-metrics/ | Five delivery-performance metrics; not story-point velocity
S04 | Argo Rollouts overview | https://argo-rollouts.readthedocs.io/ | Kubernetes progressive delivery and metric-driven promotion/rollback
S05 | Argo Rollouts FAQ | https://argo-rollouts.readthedocs.io/en/stable/FAQ | Runtime rollback does not update Git desired state
S06 | Argo Rollouts best practices | https://argo-rollouts.readthedocs.io/en/stable/best-practices/ | Validate telemetry with dry runs before production automation
S07 | SLSA verifying artifacts v1.0 | https://slsa.dev/spec/v1.0/verifying-artifacts | Verify signatures, artifact digest, trusted builder and build parameters
S08 | SLSA distributing provenance v1.1 | https://slsa.dev/spec/v1.1/distributing-provenance | Bind attestations to artifacts and preserve immutable provenance
S09 | Microsoft Cost Management budgets tutorial | https://learn.microsoft.com/en-us/azure/cost-management-billing/costs/tutorial-acm-create-budgets | Budgets do not stop consumption; cost data and evaluation are delayed
S10 | OWASP Agentic AI Threats and Mitigations | https://genai.owasp.org/resource/agentic-ai-threats-and-mitigations/ | Threat-model agent memory, tools, identities and privilege